## Sheet1
ID1 | 结束日期2 | 名称3 | 项目编号4 | 系数5 | 开始日期6 | 项目状态7 | 部门ID8 | 员工ID9 | 项目经理10 | 部门名称11 | 创建人ID12 | 创建人名称13 | 跟进级别14 | 报价生产性15 | 报价总人月16 | 反馈BUG率17 | 当前粗利润率18 | 粗利润率19 | 项目规模 20 | 项目类型21 | 预定生产性22 | 预计投入总人月23 | 合同受注状况24 | 作业范围25 | 项目评审状态26 | 财务预定完成结算时间27 | 财务完成结算时间28 | 项目结算年份29 | 结项状态30 | 财务结算状态31
810175 | 2014-03-31 00:00:00 | eAD2国民年金オンサイト(2014/5开始转为长期派遣) | 140604-1 | 1 | 2014-03-17 00:00:00 | 3 | 723327 | 0883 | 何伟新 | 第一开发本部开发一部 | 1300 | 苏佩钰 |  |  | 0.45 |  |  | 8 |  | 人员派遣 |  | 0.45 | 1 |  | 1
647730 | 2014-10-31 00:00:00 | 日立M2MネットワークS_HeadEndSystem | S140606-1-1S | 1 | 2014-06-15 00:00:00 | 3 | 634670 | 9088 | 冯杨 | 苏州开发部 | 1300 | 苏佩钰 |  | 1.31 | 5.82 |  |  | 40.2 | 7.6 | 项目委托 | 1.08 | 7.01 | 1 | 详细设计~CT，CTバグ修正 | 1
963078 | 2014-04-25 00:00:00 | H26_04ハートフレンド改修対応 | 110727-2-4 | 1 | 2014-02-11 00:00:00 | 3 | 702229 | 0866 | 冯英 | 第二开发本部开发三部 | 1300 | 苏佩钰 | B | 1.65 | 8.5 | 0.35 | 48.49 | 41.1 | 14 | 项目委托 | 2.37 | 7.1 | 1 | PC~UT | 1 |  |  | 2014 | 1 | 2
291774 | 2014-09-30 00:00:00 | eAD2法人住民税11月末リリース分 | G140820-1-1S | 1 | 2014-08-26 00:00:00 | 3 | 723327 | 0394 | 刘文育 | 第一开发本部开发一部 | 1300 | 苏佩钰 | B | 2.16 | 3.4 |  |  | 40.6 | 7.33 | 项目委托 | 2.44 | 3 | 1 | FD~CT | 1 |  |  |  | 1
227191 | 2014-04-01 00:00:00 | 番号制度対応(eAD2宛名) | 131213-1-1 | 1 | 2014-01-01 00:00:00 | 3 | 723327 | 0394 | 刘文育 | 第一开发本部开发一部 | 1300 | 苏佩钰 |  | 0 | 2.84 |  |  | 31 | 0 | 人员派遣 | 0 | 2.84 | 1 | onsite | 1
070826 | 2014-12-31 00:00:00 | eAD2法人住民税の番号利用対応 | G141008-1-1S | 1 | 2014-10-08 00:00:00 | 1 | 723327 | 0394 | 刘文育 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 2.38 | 10.3 | 0.15 |  | 42.5 | 24.54 | 项目委托 | 2.5 | 9.8 | 1 | FD~CT | 1
876863 | 2014-12-31 00:00:00 | APACシステム保守作業（第三期） | G140618-3-3S | 1 | 2014-10-01 00:00:00 | 1 | 461023 | 0207 | 刘永 | 第一开发本部开发三部 | 1300 | 苏佩钰 |  | 3.33 | 10.5 |  |  | 42.6 | 35 | 人员派遣 | 2.92 | 12 | 0 | 设计开发 | 1
125727 | 2014-09-30 14:13:10 | IFSシステム保守作業 | G140618-3-2S | 1 | 2014-07-01 00:00:00 | 3 | 461023 | 0207 | 刘永 | 第一开发本部开发三部 | 1300 | 苏佩钰 | [6 empty] | 0 | 项目委托 |  |  | 1 | 保守 | 0
252921 | 2014-01-22 00:00:00 | IFSシステム保守作業 | 110512-1 | 1 | 2011-04-21 00:00:00 | 3 | 461023 | 0207 | 刘永 | 第一开发本部开发三部 | 1300 | 苏佩钰 | [6 empty] | 0 | 项目委托 |  |  | 1 | IFS保守 | 0 |  | 2014-02-28 | 2013年下半年 | 1 | 2
078238 | 2014-07-01 00:00:00 | IFSシステム保守作業 | G140618-3-1S | 1 | 2014-01-01 00:00:00 | 3 | 461023 | 0207 | 刘永 | 第一开发本部开发三部 | 1300 | 苏佩钰 | [6 empty] | 0 | 项目委托 |  |  | 1 | 保守 | 0
905965 | 2014-12-31 00:00:00 | ADWORLD国民年金(2015年2月リリース分) | G140930-2-1S | 1 | 2014-10-13 00:00:00 | 1 | 723327 | 098 | 刘青海 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 3.76 | 17.3 | 0.15 |  | 40.3 | 65.08 | 项目委托 | 3.83 | 17 | 0 | 详细设计~CT | 1
570969 | 2014-07-25 00:00:00 | ADWORLD国民年金(2014年7月リリース分) | 120731-1-18 | 1 | 2014-04-16 00:00:00 | 3 | 723327 | 098 | 刘青海 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 2.59 | 8.2 | 0.15 |  | 39.4 | 21.2 | 项目委托 | 1.91 | 11.1 | 1 | 项目设计~CT | 1 |  |  |  | 1
621261 | 2014-09-30 14:20:23 | ADWORLD国民年金(2014年10月リリース分) | G140704-1-1S | 1 | 2014-07-15 00:00:00 | 3 | 723327 | 098 | 刘青海 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 2.73 | 24.4 | 0.15 |  | 38.9 | 66.7 | 项目委托 | 2.17 | 30.7 | 0 | 详细设计~CT | 1
005862 | 2014-04-25 00:00:00 | ADWORLD国民年金(2014年5月リリース分) | 120731-1-17 | 1 | 2014-02-20 00:00:00 | 3 | 723327 | 1084 | 叶晓梦 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 2.6 | 5.1 | 0.15 |  | 19.9 | 13.26 | 项目委托 | 1.09 | 12.13 | 1 | 详细设计~CT | 1 |  |  |  | 1
844509 | 2014-02-12 00:00:00 | ADWORLD国民年金(2014年２月リリース分) | 120731-1 | 1 | 2013-12-02 00:00:00 | 3 | 723327 | 1084 | 叶晓梦 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 2.45 | 11.9 | 0.15 | 32.78 | 33.2 | 29.13 | 项目委托 | 1.34 | 21.77 | 1 | DD~CT | 1 |  | 2014-10-31 | 2014下半年 | 1 | 2
232261 | 2014-01-19 00:00:00 | TOSS DLR配车供需表改善 | 120806-1 | 1 | 2012-07-16 00:00:00 | 3 | 548996 | 1219 | 向国华 | 第二开发本部开发一部 | 1300 | 苏佩钰 | [6 empty] | 0 | 人员派遣 |  |  | 1 |  | 0 |  | 2014-02-28 | 2013年下半年 | 1 | 2
697729 | 2014-08-30 00:00:00 | e-CRB系统应用维护_2014年度(人员派遣) | 140609-3 | 1 | 2014-01-01 00:00:00 | 3 | 548996 | 049 | 周纲 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 13 |  |  | 30 |  | 人员派遣 |  | 13 | 1 |  | 1
712974 | 2014-02-28 00:00:00 | e-CRB系统应用维护 | 090923-1 | 1 | 2013-01-01 00:00:00 | 3 | 548996 | 049 | 周纲 | 第二开发本部开发一部 | 1300 | 苏佩钰 | [6 empty] | 0 | 人员派遣 |  |  | 1 |  | 0 |  | 2014-03-30 | 2013年下半年 | 1 | 2
326434 | 2014-12-31 00:00:00 | e-CRB业务支援及维护 | G140702-1-1S | 1 | 2014-07-01 00:00:00 | 1 | 548996 | 049 | 周纲 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 14 |  |  | 40.3 |  | 人员派遣 |  | 14 | 1 | 业务支援及维护 | 1
331062 | 2014-05-16 00:00:00 | i-Dealer广告管理系统 | 140326-1-1 | 1 | 2014-03-26 00:00:00 | 3 | 548996 | 0803 | 姚利花 | 第二开发本部开发一部 | 1300 | 苏佩钰 | A | 1.47 | 7.5 |  |  | 63.7 | 11 | 项目委托 | 1.47 | 7.5 | 1 | 外部设计~系统测试 | 1 |  |  |  | 1
764368 | 2014-09-01 00:00:00 | 展示展厅系统追加开发及导入 | G140616-2-1S | 1 | 2014-06-09 00:00:00 | 3 | 548996 | 0803 | 姚利花 | 第二开发本部开发一部 | 1300 | 苏佩钰 | A | 0.88 | 8.5 |  |  | 40.1 | 7.5 | 项目委托 | 0.77 | 9.7 | 1 | 展示展厅系统追加开发及系统导入 | 1 |  |  |  | 1
352191 | 2014-04-02 00:00:00 | 供需表IE升级对应 | 120806-1-11 | 1 | 2014-03-14 00:00:00 | 3 | 548996 | 0803 | 姚利花 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 0.1612 | 0.62 |  | 25.71 | 32 | 0.1 | 项目委托 | 0.1612 | 0.62 | 1 | 编码~结合测试 | 1 |  | 2014-10-31 | 2014下半年 | 1 | 2
358649 | 2014-06-20 00:00:00 | i-Dealer广告管理系统流媒体追加 | 140326-1-2 | 1 | 2014-04-25 00:00:00 | 3 | 548996 | 0803 | 姚利花 | 第二开发本部开发一部 | 1300 | 苏佩钰 | A | 1.93 | 10.36 |  |  | 62.7 | 20 | 项目委托 |  | 9.2 | 1 | 要件设计~系统测试 | 1 |  |  |  | 1
259235 | 2014-02-13 00:00:00 | 业务支援 | 131104-1-2 | 1 | 2013-09-22 00:00:00 | 3 | 548996 | 0803 | 姚利花 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 1.95 |  |  |  | 0 | 人员派遣 |  |  | 1 |  | 0 |  | 2014-03-01 | 2013年下半年 | 1 | 2
119401 | 2014-06-30 00:00:00 | e視眼iOSアプリ開発 | B140708-1-1S | 1 | 2014-05-01 00:00:00 | 3 | 943553 | 6001 | 孙成 | 北京开发部 | 1300 | 苏佩钰 |  | 1.9 | 4.2 |  |  | 40 | 8 | 项目委托 | 2.29 | 3.5 | 1 | PC~CT | 1
489971 | 2014-08-29 00:00:00 | e視眼Androidアプリ開発 | B140708-2-1S | 1 | 2014-07-01 00:00:00 | 3 | 943553 | 6001 | 孙成 | 北京开发部 | 1300 | 苏佩钰 |  | 1.9 | 4.2 |  |  | 40 | 8 | 项目委托 | 2.29 | 3.5 | 1 | PC~CT | 1
172734 | 2014-03-31 00:00:00 | KSSOL様向け資材＆会計システム開発(2014年部分） | 130812-1-1 | 1 | 2013-05-20 00:00:00 | 3 | 634670 | 9051 | 季玥 | 苏州开发部 | 1300 | 苏佩钰 |  | 3.14 | 47.79 |  |  | -35 | 150 | 项目委托 | 2.5 | 60 | 1 | 详细设计，制造(Junit测试，UT测试) | 1
027237 | 2014-04-25 00:00:00 | 次世代開発_（兆方店展開対応（追加分）） | 140417-3-1 | 1 | 2014-04-12 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 | [6 empty] | 0 | 项目委托 |  |  | 0 |  | 1 |  |  |  | 1
648346 | 2014-04-11 00:00:00 | 次世代開発 | 130402-1-29 | 1 | 2014-02-07 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 6.92 |  |  |  | 0 | 项目委托 |  |  | 1 |  | 1 |  |  |  | 1
771257 | 2014-01-27 00:00:00 | ADAM機能追加iOS７対応 | 140110-1-1 | 1 | 2013-12-30 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 1.62 |  |  |  | 0 | 项目委托 |  |  | 1 |  | 1 |  |  |  | 1
691439 | 2014-11-21 00:00:00 | 次世代e-CRBタブレット iOS8 VersionUp対応 | G140827-1-1S | 1 | 2014-11-05 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 1.5 | 0.5 |  |  | 67.1 | 0.75 | 项目委托 | 1.5 | 0.5 | 1 | PC~号口 | 1
144113 | 2014-06-24 00:00:00 | サービス・タブレット（iPad機能）維持・保守（２０１４年No 1）(7444) | G140611-1-1S | 1 | 2014-05-19 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 1.67 | 0.9 |  |  | 21.3 | 1.5 | 项目委托 | 1.07 | 1.4 | 1 | 保守 | 1 |  |  |  | 1
379821 | 2014-02-06 00:00:00 | 次世代开发 | 111116-1-1 | 1 | 2013-12-13 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 | [6 empty] | 0 |  |  |  | 0 |  | 0 |  | 2014-03-01 | 2013年下半年 | 1 | 2
944178 | 2014-03-28 00:00:00 | 次世代開発_店舗展開 | 130402-1-28 | 1 | 2014-02-24 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 0.66 |  |  |  | 0 | 项目委托 |  |  | 1 |  | 1 |  |  |  | 1
853128 | 2014-09-30 00:00:00 | 新销售系统（售后）CVM功能追加 | G140714-1-1S | 1 | 2014-07-11 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 1.38 | 10.26 |  |  | 38.5 | 14.2 | 项目委托 | 1.11 | 12.8 | 1 | 要件设计~号口配信 | 1 |  |  |  | 1
635073 | 2014-05-16 00:00:00 | 次世代開発_（維持・保守（2013年No.2）） | 140417-2-1 | 1 | 2014-04-28 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 | [6 empty] | 0 | 保守 |  |  | 0 |  | 1 |  |  |  | 1
985198 | 2014-07-04 00:00:00 | 次世代e-CRBタブレット iOS7.1 VersionUp対応（7599-1） | G140625-2-1S | 1 | 2014-06-25 00:00:00 | 3 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 0.95 | 0.63 |  |  | 50.1 | 0.6 | 项目委托 | 0.75 | 0.8 | 1 | PC~号口 | 1
230887 | 2014-12-02 00:00:00 | GTMC_新销售系统（售后)-本地化改善 | G140624-2-1S | 1 | 2014-06-25 00:00:00 | 2 | 548996 | 1046 | 岑礼健 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 1.19 | 23.69 |  |  | 58.1 | 28.13 | 项目委托 | 1.2 | 23.4 | 0 | 新销售系统（售后)-本地化改善 | 1
669576 | 2014-01-10 00:00:00 | DLR车辆展示系统 | 131219-1-1 | 1 | 2013-11-16 00:00:00 | 3 | 548996 | 1223 | 张国富 | 第二开发本部开发一部 | 1300 | 苏佩钰 | [6 empty] | 0 | 项目委托 |  |  | 0 |  | 0 |  | 2014-02-01 | 2013年下半年 | 1 | 2
060499 | 2014-11-17 00:00:00 | ADWORLD農家台帳(2014年11月リリース分) | G140714-3-1S | 1 | 2014-07-16 00:00:00 | 3 | 723327 | 1060 | 张居爽 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A |  |  | 0.15 |  |  | 0 | 项目委托 |  |  | 0 |  | 0
775362 | 2014-04-15 00:00:00 | 艾帕克IFS服务器扩容项目 | 140328-2 | 1 | 2014-03-28 00:00:00 | 3 | 647431 | 0753 | 彭尧 | 系统集成部 | 1300 | 苏佩钰 | [5 empty] | 69 |  | 软硬件采购 |  | 0.65 | 1 | 设备采购与支付 | 1
824662 | 2014-07-31 00:00:00 | 艾帕克服务器保守维护 | G140723-1-1S | 1 | 2013-08-01 00:00:00 | 3 | 647431 | 0753 | 彭尧 | 系统集成部 | 1300 | 苏佩钰 | [6 empty] | 0 |  |  |  | 0
724633 | 2014-04-20 00:00:00 | ADWORLD受益者(2014年３月リリース分) | 120611-1-18 | 1 | 2014-01-22 00:00:00 | 3 | 723327 | 1237 | 明玄宇 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 1.6 | 3.5 | 0.15 |  | 47.2 | 5.6 | 项目委托 | 0.93 | 6 | 1 | 详细设计~CT | 1 |  |  |  | 1
217274 | 2016-12-31 00:00:00 | 长期外派日本人员 | 140528-1 | 1 | 2009-01-01 00:00:00 | 1 | 203102 | 7501 | 曾嘉良 | 日本支社 | 1300 | 苏佩钰 | [6 empty] | 0 | 人员派遣 |  |  | 0 |  | 0
889055 | 2014-05-16 00:00:00 | i-crop再构筑号口后对应 | 130913-1-5 | 1 | 2014-02-12 00:00:00 | 3 | 548996 | 0155 | 朱伟勇 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 3.6 |  | 51.33 | 50.1 |  | 项目委托 |  | 3.1 | 1 | BUG调查和对应 | 1 |  |  | 2014 | 1 | 2
402475 | 2014-02-11 00:00:00 | i-CROP再構築 | 130913-1-1 | 1 | 2013-09-09 00:00:00 | 3 | 548996 | 0155 | 朱伟勇 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 0.51 | 19.8 |  | 56.17 | 54 | 10 | 项目委托 | 0.43 | 23 | 1 | PC~TT | 1 |  |  | 2014 | 1 | 2
757573 | 2014-06-25 00:00:00 | 监控室电话线布线及电话交换机安装配置 | G140618-4-1S | 1 | 2014-06-18 00:00:00 | 3 | 647431 | 0197 | 朱树歆 | 系统集成部 | 1300 | 苏佩钰 |  |  | 0.05 |  |  | 67.6 |  | 项目委托 |  | 0.02 | 1 | 采购电话交换机、监控室电话线布线、电话交换机安装配置 | 1 |  |  |  | 1
625114 | 2014-04-11 00:00:00 | 广州世嘉智尼JUNIPER防火墙构筑 | 140325-1-1 | 1 | 2014-03-25 00:00:00 | 3 | 647431 | 0197 | 朱树歆 | 系统集成部 | 1300 | 苏佩钰 | [6 empty] | 0 |  |  |  | 0
563826 | 2014-04-30 00:00:00 | 面向销售店管理系统APP的CRPM信息汇总数据接口开发 | 140418-1-1 | 1 | 2014-04-21 00:00:00 | 3 | 548996 | 0190 | 李冠杰 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 2941.18 | 0.68 |  |  | 55.9 | 2000 | 项目委托 | 2000 | 1 | 1 | 编码、检证测试和号口 | 1 |  |  |  | 1
911554 | 2014-06-30 00:00:00 | 新销售系统导入__2014年度（人员派遣） | 140609-2 | 1 | 2014-01-01 00:00:00 | 3 | 548996 | 0190 | 李冠杰 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 13 |  | 27.34 | 30 |  | 人员派遣 |  | 13 | 1 |  | 1 |  | 2014-10-31 | 2014下半年 | 1 | 2
711847 | 2014-06-06 00:00:00 | 现行版SLIM和短信速报追加雷凌订单预售管理的改善 | 140515-1-1 | 1 | 2014-05-15 00:00:00 | 3 | 548996 | 0190 | 李冠杰 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 0.87 | 0.87 |  |  | 80.1 | 0.75 | 项目委托 | 3.75 | 0.2 | 1 | 定义书作成、编码、检证测试和号口 | 1 |  |  |  | 1
959815 | 2014-04-09 00:00:00 | i-CMS Windows7 VersionUpに伴う影響調査 | 140324-1-2 | 1 | 2014-03-25 00:00:00 | 3 | 548996 | 0190 | 李冠杰 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 1 |  |  | 66.6 | 0 | 人员派遣 |  | 1 | 1 | 结合测试 | 1 |  |  |  | 1
312654 | 2014-07-31 00:00:00 | 中古車システム画像保存先変更 | G140627-2-1S | 1 | 2014-06-27 00:00:00 | 3 | 548996 | 0190 | 李冠杰 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 0.62 | 1.45 |  |  | 62.7 | 0.9 | 项目委托 | 1.13 | 0.8 | 1 | 开发~检证测试 | 1 |  |  |  | 1
756231 | 2014-03-28 00:00:00 | 中古車e-ビジネスプラットフォーム改善に基づいてUMS側の改善開発 | 090923-2 | 1 | 2013-12-02 00:00:00 | 3 | 548996 | 0190 | 李冠杰 | 第二开发本部开发一部 | 1300 | 苏佩钰 | A | 0.98 | 11.5 |  | 56.12 | 51.1 | 11.3 | 项目委托 | 1.07 | 10.6 | 1 | 要件定义~TT | 1 |  |  | 2014 | 1 | 2
490275 | 2014-04-01 00:00:00 | iCMS系统Win7故障对应 | 140324-1-1 | 1 | 2014-03-24 00:00:00 | 3 | 548996 | 0190 | 李冠杰 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 0.65 |  |  | 84.6 |  | 项目委托 |  | 0.2 | 1 | 问题调查及代码改修 | 1 |  |  |  | 1
264404 | 2015-01-30 00:00:00 | ANA様向け POSITIVE導入（α、AWF） | S141027-1-1S | 1 | 2014-11-17 00:00:00 | 1 | 634670 | 0027 | 李甲 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 12.36 |  |  | 36.6 |  | 项目委托/人员派遣 |  | 10.25 | 1 | 制造（UT测试） | 1
994809 | 2014-02-28 00:00:00 | 日立粉末冶金様 資材システム開発 | 131209-1-1 | 1 | 2013-12-12 00:00:00 | 3 | 702229 | 0027 | 李甲 | 第二开发本部开发三部 | 1300 | 苏佩钰 | C | 1.10 | 6.23 | 0.25 | 25.94% | 33.3 | 6.36 | 项目委托 | 0.82 | 8.3 | 1 | DD~CT | 1 |  |  | 2014 | 1 | 2
756810 | 2014-06-13 00:00:00 | Salon's Mate在庫機能開発 | 140327-1-1 | 1 | 2014-04-01 00:00:00 | 3 | 702229 | 0027 | 李甲 | 第二开发本部开发三部 | 1300 | 苏佩钰 | B | 1.34 | 5.92 | 0.25 | 35.56% | offshore44+onsite39.9 | 7.935 | 项目委托 | 1.17 | 6.8 | 1 | DD~CT | 1 |  |  | 2014 | 1 | 2
806257 | 2014-04-30 00:00:00 | 地域包括ケアＶ２．５対応作業 | 101111-1-11 | 1 | 2013-12-02 00:00:00 | 3 | 702229 | 0351 | 李育安 | 第二开发本部开发三部 | 1300 | 苏佩钰 | C | 2.16 | 16.5 | 0.25 | 41.73 | 44.9 | 35.7 | 项目委托 | 2.38 | 21 | 1 | PG~UT | 1 |  |  | 2014 | 1 | 2
693779 | 2014-10-31 00:00:00 | 2014届新人技术培训 | G140905-1-1S | 0.5 | 2014-09-09 00:00:00 | 3 | 853418 | 1000 | 李萍 | 人力资源部 | 1300 | 苏佩钰 | [6 empty] | 0 |  |  |  | 0
576579 | 2015-01-31 00:00:00 | 居家养老平台系统维护 | S140930-1-1S | 1 | 2014-11-26 00:00:00 | 1 | 634670 | 9080 | 李蠡 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 0.4 |  |  | 47.7 |  | 项目委托 |  | 0.4 | 1 | 维护 | 1
429267 | 2015-04-30 00:00:00 | ANA様向け次期人事・給与システム構築 | 140414-2-2 | 1 | 2014-04-02 00:00:00 | 1 | 634670 | 9080 | 李蠡 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 130.6 |  |  | 38.1 |  | 项目委托，人员派遣 |  | 130.6 | 1 | 基本设计~综合测试 | 1
436638 | 2014-11-07 00:00:00 | ANA様向け POSITIVE導入 | S140728-1-1S | 1 | 2014-08-25 00:00:00 | 3 | 634670 | 9080 | 李蠡 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 5.75 |  |  | 38.3 |  | 项目委托 | 5.75 | 5.75 | 1 | 制造（UT测试） | 1
246585 | 2015-01-31 00:00:00 | 番号利用対応(宛名管理) | G141008-1-2S | 1 | 2014-10-20 00:00:00 | 1 | 723327 | 0817 | 李超 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | [5 empty] | 0 |  |  |  | 0
671169 | 2014-03-31 00:00:00 | eAD2収滞納 | 140214-1-1 | 1 | 2014-01-01 00:00:00 | 3 | 723327 | 0817 | 李超 | 第一开发本部开发一部 | 1300 | 苏佩钰 | B | 2.7 | 22.22 | 0.15 | 27.87 | 27.8 | 60 | 项目委托 | 1.67 | 35.9 | 1 | 项目设计~CT | 1 |  | 2014-10-31 | 2014下半年 | 1 | 2
053989 | 2014-08-22 00:00:00 | eAD2宛名 | 131213-1-2 | 1 | 2014-03-10 00:00:00 | 3 | 723327 | 0817 | 李超 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 2.65 | 56.6 | 0.2 |  | 38.6 | 150 | 项目委托 | 2.01 | 74.5 | 1 | 详细设计~CT | 1 |  |  |  | 1
783826 | 2014-06-18 00:00:00 | ADWORLD福祉作業(2014年7月リリース分) | 130919-1-3 | 1 | 2014-03-10 00:00:00 | 3 | 723327 | 0520 | 杨辉 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 2.7 | 6.5 | 0.2 |  | 38.6 | 17.52 | 项目委托 | 2.61 | 6.7 | 1 | 详细设计~UT | 1 |  |  |  | 1
800184 | 2014-02-21 00:00:00 | ADWORLD福祉作業(2014年２月リリース分) | 130919-1-2 | 1 | 2013-12-10 00:00:00 | 3 | 723327 | 0520 | 杨辉 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 2.87 | 6.7 | 0.20 | 37.48 | 37.5 | 19.21 | 项目委托 | 2.26 | 8.5 | 1 | 詳細設計～ＵＴ | 1 |  | 2014-10-31 | 2014下半年 | 1 | 2
040856 | 2014-01-10 00:00:00 | ISO27001信息安全体系内部审核 | 140318-2-1 | 0.5 | 2014-01-09 00:00:00 | 3 | 647431 | 0007 | 林超权 | 系统集成部 | 1300 | 苏佩钰 | [6 empty] | 0 | 公司内部业务 |  |  | 0 |  | 0 |  |  |  |  | 3
085689 | 2014-08-30 00:00:00 | 子育て支援のオンライン設計（二次開発）作業 | 140516-1-1 | 1 | 2014-06-02 00:00:00 | 3 | 723327 | 1305 | 江中辉 | 第一开发本部开发一部 | 1300 | 苏佩钰 |  |  | 3.15 |  |  | 33 | 0 | 人员派遣 |  | 3.15 | 1 | 设计 | 1
710128 | 2014-12-31 00:00:00 | WebTCV国内车型对应 | G140808-1-2S | 1 | 2014-10-09 00:00:00 | 1 | 548996 | 0217 | 汪扬 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 1.28 | 7.84 |  |  | 73.1 | 10 | 项目委托 | 1.92 | 5.2 | 1 | PC~ST | 1
616362 | 2014-08-21 00:00:00 | G-SLIM改善 | G140620-1-1S | 1 | 2014-06-27 00:00:00 | 3 | 548996 | 0217 | 汪扬 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 1488.10 | 4.2 |  |  | 54.6 | 6250 | 项目委托 | 1811.59 | 3.45 | 1 | PC~ST | 1 |  |  |  | 1
024315 | 2014-09-10 00:00:00 | 雷凌WEB TCV開発対応 | G140604-4-1S | 1 | 2014-07-01 00:00:00 | 3 | 548996 | 0217 | 汪扬 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 0.87 | 2.3 |  |  | 65.2 | 2 | 项目委托 | 0.89 | 2.25 | 1 | PC~CT | 1
226922 | 2014-12-22 00:00:00 | TOSS供需票改善提案 | G141106-1-1 | 1 | 2014-11-07 00:00:00 | 1 | 548996 | 0217 | 汪扬 | 第二开发本部开发一部 | 1300 | 苏佩钰 | [6 empty] | 30 | 提案 |  | 20 | 0 |  | 1
647128 | 2014-11-28 00:00:00 | iPad TCV凯美瑞小改款 | G141014-1-1S | 1 | 2014-11-03 00:00:00 | 2 | 548996 | 0217 | 汪扬 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 0.91 | 0.55 |  |  | 49.7 | 0.5 | 项目委托 | 0.5 | 1 | 1 | PC~ST | 1
675005 | 2014-02-14 00:00:00 | ADWORLD住宅(2014年２月リリース分) | 120611-1-16 | 1 | 2013-12-16 00:00:00 | 3 | 723327 | 0428 | 沈浩 | 第一开发本部开发一部 | 1300 | 苏佩钰 | C | 1.56 | 4.2 | 0.15 |  | 52.2 | 6.54 | 项目委托 | 1.92 | 3.4 | 1 | AD~CT | 1 |  |  |  | 1
062846 | 2014-06-30 00:00:00 | ADWORLD住宅(2014年7月リリース分) | 120611-1-17 | 1 | 2014-03-03 00:00:00 | 3 | 723327 | 0428 | 沈浩 | 第一开发本部开发一部 | 1300 | 苏佩钰 | C | 1.63 | 6.4 | 0.15 | 35.06 | 42.2 | 10.4 | 项目委托 | 1.37 | 7.6 | 1 | 详细设计~CT | 1 |  | 2014 -10-31 | 2014下半年 | 1 | 2
196251 | 2015-01-23 00:00:00 | ADWORLD農家台帳(2015年3月リリース分) | G141120-1-1S | 1 | 2014-11-10 00:00:00 | 1 | 723327 | 0428 | 沈浩 | 第一开发本部开发一部 | 1300 | 苏佩钰 |  | 2.44 | 7.3 |  |  | 48 | 17.8 | 项目委托 | 4.14 | 4.3 | 0 | 详细设计~CT | 1
812153 | 2014-03-28 00:00:00 | 営業支援システム改修 | 140117-1-1 | 1 | 2014-01-27 00:00:00 | 3 | 702229 | 0850 | 潘熙圣 | 第二开发本部开发三部 | 1300 | 苏佩钰 | B | 1.47 | 6.89 | 0.25 | 38.98 | 39 | 10.12 | 项目委托 | 1.37 | 7.4 | 1 | DD~CT | 1 |  |  | 2014 | 1 | 2
744399 | 2014-11-28 00:00:00 | 機器の保守契約管理システム | G140725-1-1S | 1 | 2014-08-05 00:00:00 | 3 | 398250 | 0850 | 潘熙圣 | 第一开发本部开发二部 | 1300 | 苏佩钰 | A | 2.73 | 38.93 |  |  | 8.4 | 106.18 | 项目委托 | 1.86 | 57 | 1 | PC~UT | 1 |  |  |  | 1
373313 | 2014-11-27 00:00:00 | 销售店展示信息管理系统_文件分发功能追加改善优先级2 | G140926-1-1S | 1 | 2014-09-02 00:00:00 | 2 | 548996 | 0569 | 王晖 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 1.29 | 3.11 |  |  | 40 | 4 | 项目委托 | 1.03 | 3.9 | 1 | BD~号口 | 1
948629 | 2014-11-19 09:05:52 | 统合认证本地系统对应CRPM BPKPI开发 | G140617-2-1S | 1 | 2014-06-09 00:00:00 | 3 | 548996 | 0569 | 王晖 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 0.7 | 1 |  |  | 54 | 0.7 | 项目委托 | 0.7 | 1 | 1 | BD~号口 | 1
754418 | 2014-06-27 00:00:00 | 神州数码TOP系统移动客户端开发 | 130813-1-1 | 1 | 2013-08-19 00:00:00 | 3 | 943553 | 6002 | 田国民 | 北京开发部 | 1300 | 苏佩钰 | [6 empty] | 0 | 项目委托 |  |  | 1 |  | 0
192774 | 2014-12-31 00:00:00 | 社内积分制开发 | G141201-2-1 | 0.7 | 2014-12-04 00:00:00 | 1 | 702229 | 0626 | 石莎 | 第二开发本部开发三部 | 1300 | 苏佩钰 | [7 empty] | 社内项目 |  | 3.6 | 0 |  | 1
895459 | 2014-08-06 00:00:00 | 世嘉智尼防火墙调整 | G140723-2-1S | 1 | 2014-08-06 00:00:00 | 3 | 647431 | 0588 | 粟毅 | 系统集成部 | 1300 | 苏佩钰 |  |  | 0.075 |  |  | 41.4 |  | 项目委托 |  | 0.075 | 1 | 世嘉智尼防火墙调整 | 1
372832 | 2015-03-31 00:00:00 | 星野楽器殿向け作業_Symantecソフト契約更新＆管理者サポートサービス費（2014年分） | 130412-1 | 1 | 2014-03-01 00:00:00 | 1 | 647431 | 0588 | 粟毅 | 系统集成部 | 1300 | 苏佩钰 | [6 empty] | 0 |  |  |  | 0
753475 | 2014-07-02 00:00:00 | 深圳华为Java技术顾问人员派遣 | 131225-1-1 | 1 | 2014-02-27 00:00:00 | 3 | 126300 | 055 | 罗文 | 第二开发本部开发二部 | 1300 | 苏佩钰 |  |  | 4.85 |  | 24.09 |  | 0 | 人员派遣 |  |  | 1 |  | 0 |  | 2014-10-31 | 2014下半年 | 1 | 2
778688 | 2014-06-30 00:00:00 | ADWORLD農家台帳(2014年7月リリース分) | 091118-1-40 | 1 | 2014-03-03 00:00:00 | 3 | 723327 | 0993 | 肖卫华 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 2.09 | 7.5 | 0.15 |  | 44.0 | 15.7 | 项目委托 | 1.5 | 10.5 | 1 | 项目设计~CT | 1 |  |  |  | 1
570315 | 2014-02-26 00:00:00 | ADWORLD農家台帳(2014年２月リリース分) | 091118-1-38 | 1 | 2013-12-02 00:00:00 | 3 | 723327 | 0993 | 肖卫华 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A | 1.98 | 4.7 | 0.15 |  | 37.5 | 9.3 | 项目委托 | 1.26 | 7.4 | 1 | AD~CT | 1 |  |  |  | 1
605741 | 2014-08-08 09:46:10 | 農家台帳2015年１月リリース作業向けオンサイト作業 | G140724-1-1S | 1 | 2014-07-28 00:00:00 | 3 | 723327 | 0993 | 肖卫华 | 第一开发本部开发一部 | 1300 | 苏佩钰 |  |  | 1.6 |  |  | 31.5 |  | 人员派遣 |  | 1.6 | 0 | 基本设计 | 1
243369 | 2014-04-30 00:00:00 | ＴＥＥＳ納品書機能改善支援 | 090831-1-6 | 1 | 2014-01-01 00:00:00 | 3 | 702229 | 0050 | 肖浩波 | 第二开发本部开发三部 | 1300 | 苏佩钰 |  | 4.29 | 7 |  |  | 45 | 30 | 项目委托/人员派遣 | 4.29 | 7 | 1 | 保守 | 1 |  |  |  | 1
169973 | 2014-02-28 00:00:00 | オンサイト作業 | 140604-2-1 | 1 | 2014-02-17 00:00:00 | 3 | 723327 | 1074 | 胡珊珊 | 第一开发本部开发一部 | 1300 | 苏佩钰 |  |  | 0.4 |  |  | 28.9 |  | 人员派遣 |  | 0.4 | 1 |  | 1
867078 | 2014-06-30 00:00:00 | 新MERITS(STEP3) | 140115-2-3 | 1 | 2014-03-17 00:00:00 | 3 | 398250 | 0032 | 苏炜来 | 第一开发本部开发二部 | 1300 | 苏佩钰 | C | 1.47 | 31.7 |  | 33.71% | 34.7 | 46.5 | 项目委托 | 1.18 | 39.5 | 1 | PG~UT | 1 |  |  | 2014 | 1 | 2
525662 | 2014-12-31 00:00:00 | 日立系统人员派遣 | G140910-1-1S | 1 | 2014-09-09 00:00:00 | 1 | 398250 | 0032 | 苏炜来 | 第一开发本部开发二部 | 1300 | 苏佩钰 |  |  | 4 |  |  | 42 |  | 人员派遣 |  | 4 | 1 | 人员派遣 | 1
008684 | 2014-03-31 00:00:00 | 新MERITS | 140115-2 | 1 | 2014-01-13 00:00:00 | 3 | 398250 | 0032 | 苏炜来 | 第一开发本部开发二部 | 1300 | 苏佩钰 | C | 1.74 | 7.65 | 0.35 | 24.89% | 23 | 13.31 | 项目委托/人员派遣 | 1.14 | 11.7 | 1 | PG~UT | 1 |  |  | 2014 | 1 | 2
452945 | 2014-08-22 00:00:00 | 事業計画システム追加開発 | G140807-1-1S | 1 | 2014-08-08 00:00:00 | 3 | 723327 | 0216 | 董鹏武 | 第一开发本部开发一部 | 1300 | 苏佩钰 | D | 1.17 | 0.6 | 0.25 |  | 45 | 0.7 | 项目委托 | 1.17 | 0.6 | 0 | PC~CT | 1
866112 | 2014-05-06 00:00:00 | 事業計画システム追加開発 | 130307-1-3 | 1 | 2014-02-17 00:00:00 | 3 | 723327 | 0216 | 董鹏武 | 第一开发本部开发一部 | 1300 | 苏佩钰 | C | 3.55 | 3.24 | 0.2 | 31.47 | 40 | 11.51 | 项目委托 | 2.88 | 4 | 1 | 案件调查，PC~CT | 1 |  | 2014-10-31 | 2014下半年 | 1 | 2
859470 | 2014-11-01 00:00:00 | ＨＩCORE改修売上参照権限 | G140625-1-1S | 1 | 2014-06-30 00:00:00 | 3 | 702229 | 0070 | 蒋思华 | 第二开发本部开发三部 | 1300 | 苏佩钰 | B | 1.63 | 17.2 | 0.25 |  | 43 | 28 | 人员派遣 | 1.75 | 16 | 1 | 设计~CT | 1 |  |  |  | 1
182090 | 2014-03-21 00:00:00 | 苏州分公司内部OA系统 | 140126-1-1 | 0.5 | 2014-01-13 00:00:00 | 3 | 634670 | 9043 | 许浩 | 苏州开发部 | 1300 | 苏佩钰 | [6 empty] | 0 | 社内项目 |  |  | 0 |  | 0
023643 | 2014-10-31 00:00:00 | 受発注管理Accessツール開発 | 130131-2-1 | 1 | 2013-04-22 00:00:00 | 2 | 634670 | 9043 | 许浩 | 苏州开发部 | 1300 | 苏佩钰 |  | 10.48 | 6.2 |  |  | 38.9 | 65 | 项目委托 | 10.48 | 6.2 | 1 | 保守 | 1
366845 | 2014-04-30 00:00:00 | 皇御宠物上海派遣 | 131216-1-1/3/5 | 1 | 2013-09-02 00:00:00 | 3 | 634670 | 9001 | 谢禾 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 7 |  |  |  | 0 | 人员派遣 |  |  | 1 |  | 0
562037 | 2014-01-24 00:00:00 | 客户关系管理 (CRM) 系统-上海微创 | 130723-1-1 | 1 | 2013-07-23 00:00:00 | 3 | 634670 | 9001 | 谢禾 | 苏州开发部 | 1300 | 苏佩钰 | [6 empty] | 0 | 人员派遣 |  |  | 1 |  | 0
919321 | 2014-04-02 00:00:00 | 客户关系管理 (CRM) 系统-上海微创 | 130723-1-4 | 1 | 2014-01-01 00:00:00 | 3 | 634670 | 9001 | 谢禾 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 3 |  |  |  | 0 | 人员派遣 |  |  | 1 |  | 0
922860 | 2014-05-31 00:00:00 | 上海NTTData | 131216-1-4 | 1 | 2013-11-03 00:00:00 | 3 | 634670 | 9001 | 谢禾 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 3.9 |  |  |  | 0 | 人员派遣 |  |  | 1 |  | 0
950834 | 2015-01-05 00:00:00 | 上海微创人员派遣 | 130723-1 | 1 | 2014-05-05 00:00:00 | 1 | 634670 | 9001 | 谢禾 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 6 |  |  |  |  | 人员派遣 |  |  | 1 |  | 0
828467 | 2014-04-12 00:00:00 | 客户关系管理 (CRM) 系统2-上海微创 | 130723-1-3/5 | 1 | 2013-11-24 00:00:00 | 3 | 634670 | 9001 | 谢禾 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 4.24 |  |  |  | 0 | 人员派遣 |  |  | 1 |  | 0
628551 | 2014-01-28 00:00:00 | 加油站管理系统 | 131220-1-1 | 1 | 2013-12-13 00:00:00 | 3 | 634670 | 9001 | 谢禾 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 3.1 |  |  |  | 0 | 人员派遣 |  |  | 1 |  | 0
524719 | 2014-03-31 00:00:00 | SLIM GTMCマルチクライアント切替対応（2014年3月分） | 140403-2 | 1 | 2013-12-01 00:00:00 | 3 | 548996 | 0564 | 贺飞 | 第二开发本部开发一部 | 1300 | 苏佩钰 | A | 0.01 | 17.4 |  |  | 61.2 | 0.1 | 项目委托 | 0.01 | 18 | 0 | 外部设计~系统测试 | 1
160830 | 2014-11-03 00:00:00 | TOSS建议订单回答改善Step2 | G140603-1-1S | 1 | 2014-05-21 00:00:00 | 3 | 548996 | 0564 | 贺飞 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 0.78 | 2.11 |  |  | 65 | 1.65 | 项目委托 | 0.97 | 1.7 | 1 | 要件设计~用户测试 | 1 |  |  |  | 1
812729 | 2014-05-20 00:00:00 | TOSS建议订单回答改善Step1 | 140505-1-1 | 1 | 2014-04-25 00:00:00 | 3 | 548996 | 0564 | 贺飞 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 1.74 | 2.35 |  |  | 60.9 | 4.1 | 项目委托 | 2.16 | 1.9 | 1 | 要件设计~用户测试 | 1 |  |  |  | 1
326850 | 2014-12-02 00:00:00 | 销售A卡管理系统提案 | G140617-1-1 | 1 | 2014-06-26 00:00:00 | 2 | 548996 | 0564 | 贺飞 | 第二开发本部开发一部 | 1300 | 苏佩钰 | [6 empty] | 47700 | 提案 |  | 15 | 0 |  | 1
495651 | 2014-03-28 00:00:00 | 日立アーバン改修作業 | 140210-1-1 | 1 | 2014-02-07 00:00:00 | 3 | 702229 | 0856 | 郑曙熹 | 第二开发本部开发三部 | 1300 | 苏佩钰 | C | 1.36 | 4.42 | 0.25 | 26.77% | 42.5 | 6 | 项目委托 | 1.28 | 4.7 | 1 |  | 1 |  |  | 2014 | 1 | 2
064995 | 2014-12-31 00:00:00 | 新サービス修理システム保守オフショア | 130128-1 | 1 | 2013-02-18 00:00:00 | 1 | 634670 | 9010 | 郑永福 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 35.5 |  |  | 43.3 |  | 项目委托 |  | 49.6 | 1 | PC~UT | 1
536534 | 2014-12-31 00:00:00 | eAD2収滞納 | G141008-2-1S | 1 | 2014-10-01 00:00:00 | 1 | 723327 | 0601 | 金瑶 | 第一开发本部开发一部 | 1300 | 苏佩钰 | A |  |  | 0.15 | [6 empty] | 0 |  | 0
681132 | 2014-06-30 00:00:00 | eAD2収滞納 | 140214-1-5 | 1 | 2014-04-01 00:00:00 | 3 | 723327 | 0601 | 金瑶 | 第一开发本部开发一部 | 1300 | 苏佩钰 | B | 2.88 | 19.1 | 0.15 |  | 45 | 55 | 项目委托 | 2.88 | 19.1 | 1 | 详细设计~CT | 1 |  |  |  | 1
572556 | 2014-09-30 00:00:00 | eAD2収滞納 | G140630-1-1S | 1 | 2014-07-01 00:00:00 | 3 | 723327 | 0601 | 金瑶 | 第一开发本部开发一部 | 1300 | 苏佩钰 | B | 2.93 | 18.8 |  |  | 54.1 | 55 | 项目委托 | 2.56 | 21.5 | 1 | 详细设计~CT | 1
391936 | 2014-11-30 00:00:00 | TOSS改善提案 | G140925-2-1 | 1 | 2014-09-02 00:00:00 | 3 | 548996 | 0280 | 钟惠凤 | 第二开发本部开发一部 | 1300 | 苏佩钰 | [7 empty] | 项目委托 |  | 60 | 0 | 提案 | 1
049830 | 2014-06-30 00:00:00 | bigdata | 130822-1-4 | 1 | 2014-01-01 00:00:00 | 3 | 943553 | 6000 | 陈建春 | 北京开发部 | 1300 | 苏佩钰 |  |  | 3 |  |  |  | 0 | 人员派遣 |  |  | 1 |  | 0
425921 | 2014-07-31 00:00:00 | IPTV安卓开发 | 130521-1-1 | 1 | 2014-02-18 00:00:00 | 3 | 943553 | 6000 | 陈建春 | 北京开发部 | 1300 | 苏佩钰 | [6 empty] | 0 | 项目委托 |  |  | 1 |  | 0
066763 | 2014-12-31 00:00:00 | 华夏银行测试 | 130813-1-2 | 1 | 2014-01-01 00:00:00 | 1 | 943553 | 6000 | 陈建春 | 北京开发部 | 1300 | 苏佩钰 | [6 empty] | 0 | 人员派遣 |  |  | 1 |  | 0
267965 | 2015-03-03 00:00:00 | CRPM改善要望对应 | G140905-2-1S | 1 | 2014-10-22 00:00:00 | 1 | 548996 | 0284 | 陈熙东 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  | 2.02 | 11.38 |  |  | 55.5 | 23 | 项目委托 | 1.83 | 12.6 | 1 | BD~ST | 1
330932 | 2014-07-29 00:00:00 | i-CROP側問連によるローカルシステムの影響調査 | G140714-2-1S | 1 | 2014-07-15 00:00:00 | 3 | 548996 | 0284 | 陈熙东 | 第二开发本部开发一部 | 1300 | 苏佩钰 |  |  | 0.66 |  | 63.38 | 57 |  | 项目委托 |  | 0.55 | 1 | PC~CT | 1 |  |  | 2014 | 1 | 2
044697 | 2015-02-18 00:00:00 | NTTデータ商用取引ツール開発 | G140902-1-1S | 1 | 2014-09-22 00:00:00 | 1 | 126300 | 0684 | 陈瑞庭 | 第二开发本部开发二部 | 1300 | 苏佩钰 | A | 0.78 | 9.47 |  |  | 44 | 7.4 | 项目委托、人员派遣 | 0.87 | 8.5 | 1 | 编码~UT | 1
936105 | 2014-05-13 00:00:00 | Workspro_ヨコソー | 131226-1-2 | 1 | 2014-01-01 00:00:00 | 3 | 126300 | 0684 | 陈瑞庭 | 第二开发本部开发二部 | 1300 | 苏佩钰 | B |  | 15.78 | 0.25 |  |  |  | 项目委托 |  |  | 1 | 详细设计~CT | 0 |  |  |  | 1
078019 | 2014-03-22 00:00:00 | WorksPRO消費税対応（オンサイト作業） | 140114-1-1 | 1 | 2014-01-15 00:00:00 | 3 | 126300 | 0684 | 陈瑞庭 | 第二开发本部开发二部 | 1300 | 苏佩钰 |  |  | 4 |  |  |  | 0 | 人员派遣 |  |  | 1 |  | 0
770319 | 2014-05-31 00:00:00 | 金融債権回収システム | 131231-1-1 | 1 | 2013-12-01 00:00:00 | 3 | 634670 | 0854 | 陈腾记 | 苏州开发部 | 1300 | 苏佩钰 |  |  | 30 |  |  |  |  | 项目委托 |  |  | 1 | PC~UT | 0
120501 | 2014-10-01 00:00:00 | EC構築支援 | G140625-1-2S | 1 | 2014-07-06 00:00:00 | 3 | 702229 | 0583 | 陈舜殷 | 第二开发本部开发三部 | 1300 | 苏佩钰 |  | 6.07 | 2.8 |  |  | 54 | 17 | 人员派遣 | 5.67 | 3 | 1 | 设计~CT | 1
254677 | 2016-01-01 00:00:00 | ISO9001：2008质量管理体系内部审核 | G140911-1-1S | 0.5 | 2014-09-16 00:00:00 | 1 | 429710 | 0317 | 黄丽嫦 | 品质保证部 | 1300 | 苏佩钰 | [6 empty] | 0 |  |  |  | 0
343016 | 2014-09-29 00:00:00 | ポストノーツPJ サブシステム二次開発 | G140716-2-1S | 1 | 2014-08-04 00:00:00 | 3 | 398250 | 0067 | 黄勇 | 第一开发本部开发二部 | 1300 | 苏佩钰 | A | 3.03 | 9.9 |  |  | 57.2 | 30 | 项目委托 | 3.19 | 9.4 | 1 | FD~UT | 1 |  |  |  | 1
096831 | 2014-01-31 00:00:00 | 武汉APAC IFS系统导入 | 110512-1-19 | 1 | 2013-03-01 00:00:00 | 3 | 461023 | 0067 | 黄勇 | 第一开发本部开发三部 | 1300 | 苏佩钰 |  | 1.97 | 61 |  |  | 61 | 120 | 项目委托 | 1.58 | 76 | 1 | 需求分析，系统导入，用户教育，运行支援 | 1 |  | 2014-02-28 | 2013年下半年 | 1 | 2
100513 | 2014-04-04 00:00:00 | ポストノーツＰＪサブシステム開発 | 131122-1-1 | 1 | 2013-11-29 00:00:00 | 3 | 723327 | 0067 | 黄勇 | 第一开发本部开发一部 | 1300 | 苏佩钰 |  | 6.59 | 34 |  | 29.47 | 34.9 | 224 | 项目委托 | 4.56 | 49.1 | 1 | FD~UT | 1 |  | 2014-10-31 | 2014下半年 | 1 | 2
696771 | 2014-09-30 14:12:17 | 武汉APAC IFS系统保守 | G140618-2-2S | 1 | 2014-07-01 00:00:00 | 3 | 461023 | 0067 | 黄勇 | 第一开发本部开发三部 | 1300 | 苏佩钰 | [7 empty] | 项目委托 |  |  | 1 | 保守 | 0
424055 | 2014-12-31 00:00:00 | 武汉APAC IFS系统保守（第三期） | G140618-2-3S | 1 | 2014-10-01 00:00:00 | 1 | 461023 | 0067 | 黄勇 | 第一开发本部开发三部 | 1300 | 苏佩钰 |  | 2.5 | 6 |  |  | 57.5 | 15 | 人员派遣 | 2.5 | 6 | 0 | 设计开发 | 1
468247 | 2014-06-30 00:00:00 | 武汉APAC IFS系统保守 | G140618-2-1S | 1 | 2014-02-01 00:00:00 | 3 | 461023 | 0067 | 黄勇 | 第一开发本部开发三部 | 1300 | 苏佩钰 | [6 empty] | 0 | 项目委托 |  |  | 1 | 保守 | 0
890509 | 2014-07-11 00:00:00 | 滋賀銀行殿次期為替端末開発 | 140210-2-2 | 1 | 2014-02-09 00:00:00 | 3 | 398250 | 0868 | 黄勇2 | 第一开发本部开发二部 | 1300 | 苏佩钰 | A | 2.29 | 32.4 |  | 28.16 | 32 | 74.3 | 项目委托 | 1.68 | 44.3 | 1 | PG~UT | 1 |  | 2014-10-31 | 2014下半年 | 1 | 2
503479 | 2014-07-01 00:00:00 | 丰特网络人员派遣 | G140604-3-1S | 1 | 2014-05-26 00:00:00 | 3 | 461023 | 1225 | 黄腾 | 第一开发本部开发三部 | 1300 | 苏佩钰 |  | 2.4 | 1.25 |  |  | 61 | 3 | 人员派遣 | 2.4 | 1.25 | 1 | 设计开发 | 1
893834 | 2014-02-28 00:00:00 | 移动资讯平台圈子产品化 | 130912-1-2 | 0.5 | 2014-01-10 00:00:00 | 3 | 126300 | 1225 | 黄腾 | 第二开发本部开发二部 | 1300 | 苏佩钰 | [6 empty] | 0 | 项目委托 |  |  | 1 |  | 0
264706 | 2014-02-28 00:00:00 | 中国保险家移动资讯平台圈子功能开发 | 130912-1-1 | 1 | 2013-09-06 00:00:00 | 3 | 126300 | 1225 | 黄腾 | 第二开发本部开发二部 | 1300 | 苏佩钰 |  | 3 | 10 |  |  | -100 | 30 | 公司内部研发项目 | 3 | 10 | 0 | 需求分析~CT | 1

## Sheet2
SELECT infox_project_project.id, infox_project_project.endDate, infox_project_project.`name`, infox_project_project.projectNum, infox_project_project.quot, infox_project_project.startDate, infox_project_project.`status`, infox_project_project.DEPT_PID, infox_project_project.EMP_ID, infox_sysmgr_emp.truename, infox_sysmgr_org_dept.fullname, infox_project_project.createrId, infox_project_project.createrName, infox_project_project.gjjb, infox_project_project.project_bjscx, infox_project_project.project_bjzry, infox_project_project.project_buglv, infox_project_project.project_cclrl, infox_project_project.project_clrl, infox_project_project.project_gm, infox_project_project.project_type, infox_project_project.project_ydscx, infox_project_project.project_yjtrzry, infox_project_project.shouzhu, infox_project_project.taskScope, infox_project_project.xmpjzt, infox_project_project.cwydwcjssj, infox_project_project.cwwcjssj, infox_project_project.xmjsnf, infox_project_project.jxzt, infox_project_project.jiesuan FROM infox_project_project LEFT JOIN infox_sysmgr_emp ON infox_project_project.EMP_ID = infox_sysmgr_emp.id LEFT JOIN infox_sysmgr_org_dept ON infox_project_project.DEPT_PID = infox_sysmgr_org_dept.id WHERE infox_project_project.`status` <> 5 ORDER BY infox_sysmgr_emp.truename ASC